## Sheet1
BUILD A STOCK TREND PREDICTION WEB APPLICATION IN PYTHON USING STREAMLIT
TASK | START DATE | END DATE | DURATION
Topic selection | 2022-06-06 | 2022-06-07 | 1
Problem and objectives formulation | 2022-06-07 | 2022-06-10 | 3
Requirement gathering | 2022-06-11 | 2022-06-12 | 1
Review on requirement gathered | 2022-06-12 | 2022-06-13 | 1
Gaining prerequisite knowledge | 2022-06-14 | 2022-06-16 | 2
Assinging responsiblities | 2022-06-17 | 2022-06-18 | 1
Selection of stock priceprediction algorithms | 2022-06-19 | 2022-06-21 | 2
Selection of dataset | 2022-06-22 | 2022-06-24 | 2
Coding part on jupyter notebook | 2022-06-25 | 2022-06-30 | 5
Working on STREAMLIT web application | 2022-07-01 | 2022-07-05 | 4
Analysis /design improvement | 2022-07-06 | 2022-07-09 | 3
Testing of model | 2022-07-10 | 2022-07-12 | 2
Submission of final project | 2022-07-13 | 2022-07-15 | 2
BUILD A STOCK TREND PREDICTION WEB APPLICATION IN PYTHON USING STREAMLIT